## time_estimation_sheet
Phase | Task Summary | Key Deliverables | Estimated Hours | Actual Hours | Notes | Commit Tag
0 | Project Planning & Setup | Time estimation CSV, documentation review, sample data analysis | 2.5 | 1 hr | Initial planning and understanding requirements | v0.0-planning
1 | Backend Boilerplate Setup | FastAPI project structure, database config, requirements.txt, directory structure | 3.5 | 30 min | Initialize backend with SQLAlchemy and proper folder organization | v0.1-backend-init
2 | Database Models & Schemas | Session File and ValidationResult models, Pydantic schemas, migrations | 3 | 45 min | SQLAlchemy models with relationships and request/response schemas | v0.2-db-models
3 | Core API Endpoints | Session CRUD, file upload, analysis trigger, results retrieval, error handling | 7.5 | 2 hrs | All REST endpoints for session and file management | v0.3-api-crud
4 | API Testing with Postman | Postman collection, test all endpoints, document issues | 3 | 30 min | Verify API functionality before building parsers | v0.4-api-test
5 | PDF Parser Service | pdfplumber integration, extract job/work instruction, parse Seq 20 section, extract serials and part numbers | 8 | 2 hr | Complete Traveler PDF parsing with table extraction | v0.5-pdf-parser
6 | OCR Service for Images | Tesseract setup, image preprocessing, pattern extraction, flight status detection, accuracy tuning | 8.5 | 8 hrs | Image OCR with preprocessing pipeline for serial numbers | v0.6-ocr
7 | Excel BOM Parser Service | Pandas integration, header detection, column extraction, data cleaning, multi-BOM support | 5.5 | 4 hrs | Parse 1-4 Excel files and extract Job/Part/Revision | v0.7-excel
8 | Data Normalization Service | Serial normalizer (INF/VGN), revision normalizer, part number normalizer, unit tests | 4.5 |  | Normalize all data formats for accurate comparison | v0.8-normalize
9 | Validation Engine | Implement all 7 validation checks, overall status logic, evidence collection, testing | 10.5 |  | Core validation logic with Pass/Warning/Fail/Info determination | v0.9-validation
10 | WebSocket for Progress Updates | WebSocket endpoint, progress broadcasting, connection handling, testing | 4 |  | Real-time progress updates during analysis | v0.10-websocket
11 | Frontend Boilerplate Setup | React + Vite setup, MUI installation, React Router, Axios config, directory structure | 3.5 |  | Initialize frontend with Material-UI and routing | v0.11-frontend-init
12 | File Upload Component | Drag-drop zone, file validation, upload progress, file list display, start button, error handling | 6 |  | Complete upload UI with react-dropzone | v0.12-upload-ui
13 | Progress Tracker Component | WebSocket connection, progress bar, stage indicator, modal dialog | 4 |  | Real-time progress display during analysis | v0.13-progress
14 | Results Dashboard | Overall status badge, validation checks list, color coding, evidence viewer, side-by-side comparison | 7.5 |  | Main results display with expandable check details | v0.14-results
15 | History Browser | History list table, session details, click to view, filter and search | 5 |  | Browse past analysis sessions | v0.15-history
16 | Export Feature (Extra) | CSV export button, backend endpoint, CSV formatting, file download, testing | 5 |  | Smart CSV export with all validation data | v0.16-export
17 | Frontend-Backend Integration | API service layer, connect all components to backend, error handling, end-to-end testing | 8 |  | Complete integration and testing of full flow | v0.17-integration
18 | Docker Containerization | Backend Dockerfile, frontend Dockerfile, docker-compose.yml, nginx config, environment setup, testing | 7.5 |  | Full Docker setup with one-command deployment | v0.18-docker
19 | Testing with Sample Data | Test all cases (happy path, missing files, wrong job, wrong part, rev differences), bug fixes | 5 |  | Comprehensive testing with provided sample files | v0.19-testing
20 | Deployment | Platform selection, backend deployment, frontend deployment, database setup, CORS, SSL, testing | 7.5 |  | Deploy to Render/Railway/AWS and verify | v0.20-deploy
21 | Documentation | README with setup instructions, ARCHITECTURE.md, API docs, code comments, limitations, future improvements | 7 |  | Complete project documentation | v0.21-docs
22 | Demo Video | Script writing, screen recording, editing, upload to YouTube/Loom | 3 |  | 5-minute demo showing all features | v0.22-demo
23 | Final Review & Submission | Code review, git history check, acceptance criteria verification, final deployed test, submission prep | 5 |  | Final quality check and deliverable preparation | v0.23-final
113.5 hours